## Cover
IDAHO PUBLIC CHARTER SCHOOL COMMISSION
PRE-OPENING CHECKLIST
w w w w w
Idaho Public Charter School Commission
304 North 8th Street, Room 242
Boise, Idaho 83702
Phone: (208) 332-1561
chartercommission.idaho.gov
Alan Reed, Chairman
Tamara Baysinger, Director

## Dashboard
School Name: |  | Primary Contact: |  |  | CONTINUOUS TOTAL ACCEPTED OFFERS
Intended Opening Date: |  | Primary Phone: |  |  | Month | Feb | Apr | Jun | Aug
Date Last Updated: |  | Primary Email: |  |  | # Accepted
[5 empty] | Growth Rate |  | #DIV/0! | #DIV/0! | #DIV/0!
Mission Statement:
Lottery Date:
ENROLLMENT TRACKER
BOARD MEMBERS |  |  |  |  | Grade | Accepted Offers | Offers Out | Waiting List | Total Engagement | Enrollment Cap | % of Projections
Name | Office/Committee | Term(MM/YY-MM-YY) | Email | Phone | K |  |  |  | 0 | 50 | 0%
[5 empty] | 1 |  |  | 0 | 0 | 50 | 0%
[5 empty] | 2 |  |  |  | 0 | 50 | 0%
[5 empty] | 3 |  |  |  | 0 | 50 | 0%
[5 empty] | 4 |  |  |  | 0 | 50 | 0%
[5 empty] | 5 |  |  |  | 0 | 50 | 0%
[5 empty] | 6 |  |  |  | 0 | 50 | 0%
[5 empty] | 7 |  |  |  | 0 | 0 | #DIV/0!
[5 empty] | 8 |  |  |  | 0 | 0 | #DIV/0!
[5 empty] | 9 |  |  |  | 0 | 0 | #DIV/0!
[5 empty] | 10 |  |  |  | 0 | 0 | #DIV/0!
[5 empty] | 11 |  |  |  | 0 | 0 | #DIV/0!
KEY HIRES |  |  |  |  | 12 |  |  |  | 0 | 0 | #DIV/0!
Name | Role | Hire Date | Emil | Phone | Totals | 0 | 0 | 0 | 0 | 350 | 0%
School Leader
| Business Manager |  |  |  | Self-Reported Demographics (collected via registration paperwork)
Other Hires | Intended FTE | Hired FTE | Notes | % Hired |  | Am. Indian | Asian | Black | Hispanic | White | ELL
Certified K-2 |  |  |  | #DIV/0! | Number
Certified 3-6 |  |  |  | #DIV/0! | % | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Certified 7-8 |  |  |  | #DIV/0!
Certified 9-12 |  |  |  | #DIV/0! | Demographics Collected at Records Request |  |  |  | * blue = hard coded
Special Education |  |  |  | #DIV/0! |  | FRL | SpecEd |  | *yellow= adjusted each meeting
Paraprofessional |  |  |  | #DIV/0! | Number
Office |  |  |  | #DIV/0! | % | #DIV/0! | #DIV/0!
Maintenance |  |  |  | #DIV/0!
Kitchen |  |  |  | #DIV/0!
Other (totaled) |  |  |  | #DIV/0!

## Opening Assurances
New School Pre-Opening Requirements
The following items must be collected by the PCSC for your school's files.
ITEM | COLLECTION BY PCSC
Performance Certificate Executed
Bylaws Executed
Articles of Incorporation
Conflict of Interest and/or Code of Ethics Statement
Facility Lease or Mortgage Executed
Annual Board Approved Budget
501c3 Approval Letter
Org Chart
Completion of Pre-Opening Board Training and Operational Year 1 Development Plan
Board Member and School Leader Contact Information (PCSC Dashboard)
Emergency Incident Team Communication Plan
The tasks referenced below are detailed on the following pages. The lists include tasks related to requirement for opening as well as tasks representing best practices in new school launch. While each school's pre-opening process is expected to be different, all schools must satisfactorily address all tasks listed.
ITEM | PCSC Verification
Enrollment is Sufficient for Operation
Meeting 1 Tasks Generally Complete (see "Pre-Opening Checklist", "Meeting 1 - October" tab)
Meeting 2 Tasks Generally Complete (see "Pre-Opening Checklist", "Meeting 2 - December" tab)
Meeting 3 Tasks Generally Complete (see "Pre-Opening Checklist", "Meeting 3 - February" tab)
Meeting 4 Tasks Generally Complete (see "Pre-Opening Checklist", "Meeting 4 - April" tab)
Meeting 5 Tasks Generally Complete (see "Pre-Opening Checklist", "Meeting 5 - June" tab)
Full scope of compliant school policies adopted and accessible
Final Tasks and Facilities Visit (See "Pre-Opening Checklist", "Final Facilities Visit - August" tab)
Certificate is hereby given that all facts and representations on this assurance document are true and correct.
Printed Name and Title of Authorized Charter School Representative
Signature | Date
Printed Name of PCSC Representative
Signature | Date

## Governance
Governing Board Development Sample Plan
Below is a sample outline for a charter school governing board based on best practices across the country. This is not a requirement, but hopefully can be a resource for you as you continue to refine your governance skills or bring on new board members. The timeline indicates a possible sequence, and the description column lists some of the sub-topics your board might choose to review within a given category.
CATEGORY | TRAINING TOPICS | RECOMMENDED TIMELINE | VERIFICATION
Open Meetings Law | Id 74-2 ; including: meeting notifications, quorum, agenda posting, minute maintenance, motion documentation, and executive session | September
Roberts Rules | including: motions, discussions, public participation, etc. | October
Officers and Committees | job descriptions for officers and committees | November
Public Records Requests | including: role as a public entity, communications publically accessible, and procedures for receiving and processing records requests | December
Governance vs. Management | including: differentiating the work of "founding" from the role of "governing" from the role of "managing". Identify and clarify roles for school admin and board members. Differentiate between board member's authority as an individual and as a member of the board. | January
Financial Oversight | including: training for board members regarding how to read their specific financial reports as well as understanding the school's annual report from the authorizer. | February
Meaningful Mission and Vision Establishment | High quality mission and vision statements are crucial to school success. The work to be done here is far more than endless word-smithing. Take the time to create a center that will hold when things get busy. | March
Academic Achievement | Training should address the school's assessment plan, performance standards for continued authorization and/or accreditation, current plans for supporting student success, current goals, and a timeline for when data will be presented to the board for review. benchmark data should be presented regularly to keep the board informed of progress prior to ISAT scores. | April
School Leader Evaluation | Training should address the state required administrator evaluation process and tools. The board will need to establish a timeline and make any reasonable adjustments to the process necessary to support and evaluate the performance of the school leader with respect to the uniqueness of the school's model | May
Board Maintenance | training should cover self assessment tools as well as succession plans (what skills you have vs. what you need). It should address the board member recruitment process as well as the onboarding procedures. New Director Orientation and Termination | June
Comments:

## All Tasks - Sortable
October | Finance | Performance Certificate executed. Please note, any adjustments the board may want to make to this content require an amendment of the certificate. Contact Kirsten Pochop with questions. | Y | Fully executed copy on file with the PCSC.
October | Governance | Bylaws executed. | Y | Executed copy of bylaws and meeting minutes evidencing adoption
October | Governance | Articles of Incorporation (to be filed with Secretary of State) | Y | Executed Copy. PCSC will verify this online.
October | Governance | Board Term Sheet/ Conflict of Interest Statement / Code of Ethics (33-5200 ; 74-404) | Y | Signed by Each Board Director
October | Governance | Independent Legal Counsel Secured | Y | Meeting Minutes evidencing Approval of Engagement
October | Governance | 501c3 (file the IRS form 1023. This is a lengthy application and costs approx. $1K. Please work with your legal counsel.) For planning purposes - the 1023 application requires that documentation such as executed bylaws, conflict, and articles of incorporation are already finalized. | Y | Approval or Interim Approval letter from the IRS (the final letter can take months to arrive, for most purposes the interim letter is sufficient)
October | Governance | Notification to Office of State Board of Education of Petition Approval. This is required by statute to come from the school board. Please address to Alison Henken (alison.henken@osbe.idaho.gov) and cc Jenn Thompson (jenn.thompson@osbe.idaho.gov). |  | Discussion.
October | Operations (Lead Admin) | Review procurement requirements and ensure your school proceeds appropriately. This is necessary for nutrition, transportation, IT, and other large purchases. I.C. 67-2806; see also a good summary from the SDE's Nutrition program here: https://www.sde. |  | Discussion
October | Operations (Lead Admin) | Meet with Building Safety Team - all schools are evaluated on safety and security every 3 years. The resulting report provided by the Department of Building Safety is a confidential document between the school board and the DBS. All schools are evaluated every year on building maintenance, safety and egress. They review based on 650 points of assessment, presenting a graphic to help your team make informed decisions about financial investments. (hint - the answer is not cameras). Contact Mike within 60 days of opening to have an early discussion on safety concerns as you begin your facilities project. |  | Discussion. Mike Munger School Safety Analysist Office of School Safety and Security - mike.munger@dbs.idaho.gov | Would you like me to try to schedule this as part of the December pre-opening meeting?
October | Governance | New School Form. This form is available from Michelle Clement Taylor and due to her in January. This form establishes your school and LEA operational numbers with the SDE and ensures you are eligible to received funds. You'll need your EIN and DUNS numbers complete before you submit this document. |  | Discussion
October | Enrollment (Registrar) | Comprehensive Recruitment Plan |  | Discussion
October | Enrollment (Registrar) | Compliant and Accessible Student Enrollment Application (considers potential language barriers and/or access to technology as well as efficiency and security of data collection) |  | Discussion
October | Operations (Lead Admin) | Consider a 5-Year IT plan |  | Discussion
October | Operations (Lead Admin) | It is recommended that you begin working on a transportation plan now. The procurement process is lengthy and many charters experience difficulty with bus and driver shortages. |  | Discussion
October | Governance | Review board training expectations and timeline. Evidence that all board members have completed the required trainings as well as a presentation of a year 1 plan are due in April. |  | Discussion
October | Special Populations | Intro to the Special Education Readiness review will be conducted by the SDE in the August before you open. This is based on the Special Education Manual. We will review this with the board in October and again in April. Please ensure that your board has read this documentation and that the school is fully prepared (including adopted board policy, child find and RtI programs, appropriate forms, and new student records review). |  | Discussion
October | Governance | Policy Development. School boards must adopt a full scope of policies. A full collection of policies are available from the ISBA with membership. (charter specific, reviewed 2018, but still need full review and minor adaptation from the board. ISBA recommends this process take several months). |  | Discussion
October | Operations (Lead Admin) | Website Development. A few items are required to be posted regularly on your website. This is evaluated every year and reflected on your annual report. |  | Discussion.
October | Governance | School Leader Evaluation Process. The SDE has required tools and procedures. We will revisit this in April. |  | Discussion.
October | Operations (Lead Admin) | Wellness Plan/ Policy (required for NSLP compliance, but not until July after first op year. Recommended that you get this in place asap as it can be positive leverage for grants and will be easier to implement from the beginning). See SDE descriptions and resources here: http://www.sde.idaho.gov/cnp/hne/wellness.html |  | Discussion | Eligibility Manual for School Meals
December | Finance | Finance Policy review, particularly internal controls. | Y | Document Review
December | Finance | Bank Account Established |  | Discussion
December | Finance | Signatories Identified (best practice is 2 required, but 3 identified) |  | Meeting minutes evidencing appointment.
December | Finance | salary scale developed (considers fair hiring practices and local hiring competition) |  | Discussion of Plan
December | Finance | EIN number established (state Tax ID number) |  | Verify Number exists
December | Finance | DUNS number established (required for eligibility to receive government dollars) |  | Verify Number exists
December | Enrollment (Registrar) | Comprehensive Recruitment Plan |  | Discussion of Plan
December | Enrollment (Registrar) | Compliant and Accessible Student Enrollment Application (considers potential language barriers a/o access to technology as well as efficiency and security of data collection). | Y | Discussion of Plan | SDE has a template for this form
December | Operations (Lead Admin) | Staffing plan should be fully established and comprehensive. This should reflect enrollment projections, anticipated demographics, model specific needs, and budgets. It should also include clear trigger points for hiring prior to the first year (i.e. how will you know you can hire a 2nd teacher or a counselor and how will you balance that with the natural hiring season?) |  | Discussion of Plan (recording on dashboard tab) | See IDAPA 08.02.02 for staffing certification needs
December | Operations (Lead Admin) | job descriptions for general positions are generally representative of duties. A full collection of job descriptions are available from the ISBA with membership. |  | Document Review | See IDAPA 08.02.02 for staffing certification needs
December | Operations (Lead Admin) | Release of Information on Past Job Performance. Ensure that you have a plan for checking references and documenting fair hiring practices, prior to hiring any employee (including admin). This generally includes board adoption of policy before you can interview. |  | Document review | 33-1210
December | Operations (Lead Admin) | Provide an update on the schools technology plan/progress. |  | Discussion of Plan | Erate Flow chart
December | Operations (Lead Admin) | Stakeholders must have adequate access to appropriate school personnel. Many schools adopt communication/grievance procedures that include clear documentation. This will also require that the staff reporting structure is clear. | Y | A copy of the school's org chart will need to be provided to the PCSC for our files. The PCSC will also verify that grievance procedures and contact information is appropriately noted on your website.
December | Operations (Lead Admin) | Curriculum Selection Process (should evidence research and stakeholder input as well as a plan for regular review regarding efficacy) |  | Discussion of Plan | consider: IC 33-512A
December | Academics | data analysis / Assessment plan |  | Discussion of Plan
December | Special Populations | Home Language Survey (a section of the registration paperwork) SDE has a state wide required document. |  | Document Review | http://www.sde.idaho.gov/el-migrant/el/index.html
December | Governance | Board Meeting Calendar (high level evidence that the board is planning for key work such as, administrator evaluation process, academic performance review, the audit report, etc.) |  | Document Review
December | Governance | Job Descriptions for Board Officers (chair, secretary, treasurer, etc.) and Committees (governance, academic, finance, etc.) |  | Document Review
December | Governance | Meeting Agendas posted Accurately |  | Process and Document Review | Open Meetings Law
December | Governance | Board Meeting Minutes (format consistent, content sufficient, see open meetings law) | Y | Several Examples will be required throughout the pre-operational year
December | Governance | Board Member Succession, Orientation, and Termination Process |  | Process review based on bylaws.
December | Enrollment (Registrar) | Review the enrollment procedures guidance document and ensure timelines are in place and planned procedures are compliant. |  | Discussion
December | Operations (Lead Admin) | Business Manager Hired |  | Discussion
December | Operations (Lead Admin) | Administrator hired (process needs to evidence fair hiring practices) |  | Process or Policy Review
February | Governance | Policy adoption progress review. Bring copies/ or digital access to all board approved policies to date. | Y | Document Review
February | Finance | PO Process Outlined (for admin, board, and staff if different) |  | Discussion of Plan
February | Finance | reimbursement request forms and process established |  | Document Review
February | Enrollment (Registrar) | Records Request process. It is common to include the reference to the applicable statute on the document. See I.C. 33-209 |  | Document Review | Does Michelle have an example of this?
February | Finance | Kitchen Capital Purchases (warming ovens, smallwares, etc.). Contact the SDE Nutrition department to ensure your planned service area meets the requirements for food safety, serving, and point of sale. |  | Discussion
February | Enrollment (Registrar) | Notification of lottery date posted |  | PCSC Staff will verify this on school's website
February | Enrollment (Registrar) | First offer notification and expiration process is developed. |  | Discussion/Document Review
February | Enrollment (Registrar) | Registration paperwork is compliant |  | Document Review
February | Enrollment (Registrar) | Student record receipt and processing practices should be ready to go. This will be a significant amount of time after the lottery, and it will matter that you have clear procedures before you begin |  | Discussion | health and welfare can provide training to schools regarding immunizations.
February | Operations (Lead Admin) | salaried contract established and compliant |  | Document Review
February | Operations (Lead Admin) | hourly contract established and compliant |  | Document Review
February | Operations (Lead Admin) | Time-off request forms/ process developed |  | Document Review
February | Operations (Lead Admin) | playground safe practices outlined (student expectations for outdoor play and supervision plan/expectations. Document should reflect how this information is presented to teachers/students or playground attendants) |  | Document Review | Resources: https://schoolsafety.dbs.idaho.gov/repository/playgrounds/
February | Operations (Lead Admin) | medical administration plan (policy recommended; documents should include statement of policy, administration tracking chart, and parent signature line. Options for nurse/admin administration as well as student self admin - i.e. diabetes, inhaler, or epi pen) |  | Document and Process review
February | Operations (Lead Admin) | Contact the Federal Programs Office (Elmira Feather) at the SDE and notify them of your school's primary contact. They will get you set up with a login in for their system. In March you'll provide an estimate of low income students and in April you'll be able to see an estimated allocation. If you choose to take this allocation, formal reporting is due by end of June. |  | Discussion
February | Finance | Annual Budget Approval Process Review the SDE template for newspaper publication. Must have a hearing 30 days prior to the July regular meeting for each school. Board must be approved in July and is due to the PCSC and the SDE by July 15th. SDE require
February | Operations (Lead Admin) | Materials Safety Data Sheet (MSDS) utilized appropriately through the school (any chemicals need to be stored appropriately and usage must be tracked according to these guidelines. Mostly applies to chemistry supplies, but may also apply to janitorial or art supplies. This will matter for fire safety and health inspections. verify that your school is compliant if applicable) |  | Document and Process review (if applicable)
February | Enrollment (Registrar) | SIS system set up. Review of ISEE report data and report due dates. Be prepared to begin building a calendar of reminders for the upcoming school year. |  | Discussion
February | Finance | Facility Lease or Mortgage Executed | Y | Fully Executed Copy on File at PCSC and School
February | Finance | Accounting System Secured and Set up |  | Discussion
February | Enrollment (Registrar) | Records tracking for special services process
February | Operations (Lead Admin) | Asset tracking and Materials Receipt Process |  | Discussion
February | Enrollment (Registrar) | Student File Compliance Check |  | Student File plan review/feedback; file spot check in August
February | Operations (Lead Admin) | facilities safety checklists (indoor and outdoor) established |  | Document Review
February | Operations (Lead Admin) | Crisis Management Plan (review with your local emergency responders the summer before opening; start early as a quality plan will take several months to develop) (plan should include training materials, quick reference guide, evacuation maps, recovery plans. resources can be found here. | Y | PCSC will need a copy of your "Incident Team" org chart with roles defined and your "Recovery Plan" timeline. We will also need to be included on your emergency notification system (whether that is text system, phone tree, or email distribution system). | Include also, a plan for youth suicide prevention and safe and drug free schools. Guidance on both topics can be found here: http://www.sde.idaho.gov/student-engagement/index.html
February | Operations (Lead Admin) | drop off and dismissal procedures established (evidence should reflect how this information is shared with families as well as supervision expectations) . The PCSC can provide resources. |  | Document Review
April | Governance | Policy adoption progress review. Bring copies/ or digital access to all board approved policies to date. | Y | Document Review
April | Enrollment (Registrar) | Student information system implementation update |  | Discussion
April | Operations (Lead Admin) | payroll and timecard systems adopted |  | Discussion
April | Operations (Lead Admin) | Substitute process established |  | Discussion
April | Operations (Lead Admin) | Health Benefits Secured |  | Discussion
April | Operations (Lead Admin) | Retirement Benefits Secured |  | Discussion
April | Operations (Lead Admin) | New Hire Process Established (paperwork, legal, payroll, benefits, etc.) |  | Document Review. A sample new-hire checklist is sufficient.
April | Operations (Lead Admin) | New Hire Orientation Established (should consider certified and classified staff and evidence plans for beginning of year as well as mid-year hires) |  | Discussion
April | Operations (Lead Admin) | PCSC Reporting Calendar Reviewed |  | Discussion
April | Operations (Lead Admin) | SDE Reporting Calendar Reviewed and Special Education, and OSBE |  | Discussion | Special Education: http://www.sde.idaho.gov/sped/files/shared/Special-Education-Important-Dates.pdf OSBE: Continuous Improvement Plan; Literacy Intervention program Plan, and College and Career Advising and Mentoring Plan https://boardofed.idaho.gov/k-12-education/school-district-charter-school-planning-training/; ISEE Data Monthly Submission Schedules: https://www.sde.idaho.gov/tech-services/isee/files/general/program/Data-Monthly-Submission-Schedules.pdf
April | Operations (Lead Admin) | Stakeholder Reporting Calendar Established (should evidence report cards, state of the school address, stakeholder survey timelines, etc.) |  | If this type of information is embedded in your published school calendar, no further evidence is necessary.
April | Operations (Lead Admin) | Principal's Repot (to Board) Plan (i.e. data dashboard) Best practices include a standard set of data reported to the governing board by the school principal each meeting. This data should reflect progress toward established goals, and attempt to reflect the board's administrator evaluation process. |  | Discussion of Plan/ Document Review
April | Operations (Lead Admin) | Community Meeting Plan (assemblies) |  | If this information is embedded in your daily schedule, no further evidence is required. If not, discussion.
April | Operations (Lead Admin) | Community Event Plan (student work showcases, conferences, etc.) |  | if this information is embedded in your published school calendar, no further evidence is necessary. If not, discussion.
April | Academics | school-wide professional development plan (should include plus with time sufficiently reflected in the calendar and daily schedule) |  | Document Review | 08.02.02 includes some specific requirements.
April | Academics | Teacher coaching plan (reflecting how individual needs will be met beyond the school-wide PD plan) |  | Document Review
April | Academics | Teacher formal evaluation tools |  | Document Review | 08.02.02
April | Special Populations | Special Education Director Identified |  | Discussion regarding qualifications, start date, and plan for student intake and paras.
April | Special Populations | 504 coordinator identified |  | Discussion regarding qualifications, start date, and time allocation
April | Operations (Lead Admin) | NSLP application approved (if applicable) |  | Discussion
April | Operations (Lead Admin) | common behaviors description are communicated. (transitions, bathrooms, cafeteria, etc.) |  | Document Review
April | Operations (Lead Admin) | Positive Behavior Plan (this is in extension of the formal discipline policies and should evidence the school's day to day philosophy and procedures for classroom management) |  | Document Review
April | Operations (Lead Admin) | Annual Calendar | Y | Board Approved Final Copy
April | Operations (Lead Admin) | Daily Schedule | Y | Board Approved Final Copy
April | Operations (Lead Admin) | Extra Curricular Plan Established (if applicable) |  | Discussion
April | Operations (Lead Admin) | After school Care Plan Established (if applicable) |  | Discussion
April | Operations (Lead Admin) | Review the estimated federal programs allocation, provided by the federal programs department and decide whether you intend to pursue the funds. |  | Discussion
April | Operations (Lead Admin) | Website Compliance Check |  | PCSC will verify online at various times
April | Special Populations | Review of readiness for special education. | Y | Please bring meeting minutes evidencing adoption of the special education manual and special education policies, copies of all policies, forms. You may want to bring your special education director (or intended) to this meeting to discuss plans for staff training and records review. |  | IEP Guidance Handbook
April | Governance | Board Member Training | Y | Evidence that all board members have completed the required trainings and a copy of the year 1 development plan is due to the PCSC
April | Operations (Lead Admin) | Building maintenance safety check |  | https://schoolsafety.dbs.idaho.gov/10yearplans/
April | Academics | Curriculum Map for first year (minimally) | Y | Document Review
April | Finance | Consolidated Federal and State Grant Applications. Contact SDE- Elmira Feather, due on 5/1. |  | Discussion
April | Governance | New Charter School Boot camp. Admin, Business Manager, program directors, and board members are invited, please talk with Michelle Clement-Taylor for more information. |  | Discussion
April | Academics | First two weeks curriculum plan process |  | Document Review
June | Special Populations | Review of Special Education Readiness Plan (including child find, RtI, and at-risk identification procedures) |  | Discussion of Plan/ Document Review
June | Governance | School Leader Evaluation Tools | Y | Document (if modified from SDE)
June | Finance | Transportation Contract Executed |  | Meeting Minutes evidencing contract award or authorization for signatory
June | Finance | Landscaping/Snow Removal Contract Executed |  | Meeting Minutes evidencing contract award or authorization for signatory
June | Finance | Special Services (speech, OT, etc.) Identified and retained |  | Meeting Minutes evidencing contract award or authorization for signatory
June | Finance | Independent Auditor Contract Executed |  | Meeting Minutes evidencing contract award or authorization for signatory
June | Finance | IT Contract Executed (if applicable) |  | Meeting Minutes evidencing contract award or authorization for signatory
June | Finance | D&O Insurance Policy Secured | Y | Meeting Minutes evidencing contract award or authorization for signatory.
June | Finance | Property and Liability Insurance Secured |  | Meeting Minutes evidencing contract award or authorization for signatory
June | Finance | Workers Compensation Insurance Secured |  | Meeting Minutes evidencing contract award or authorization for signatory
June | Finance | monthly finance reports established for board |  | Document Review
June | Enrollment (Registrar) | Family orientation process |  | Discussion
June | Enrollment (Registrar) | New student beginning of year process |  | Discussion
June | Enrollment (Registrar) | New student mid-year process |  | Discussion
June | Enrollment (Registrar) | Records tracking for special services process |  | Discussion
June | Academics | Assessment Coordinator Identified |  | Discussion regarding qualifications, start date, and sufficient time allocation.
June | Operations (Lead Admin) | Asset tracking and Materials Receipt Process |  | Discussion
June | Special Populations | ELL coordinator identified |  | Discussion regarding qualifications, start date, and plans for reviewing student records.
June | Operations (Lead Admin) | drop off and dismissal procedures established (evidence should reflect how this information is shared with families as well as supervision expectations) |  | Discussion
June | Operations (Lead Admin) | FRL application process established |  | Discussion
June | Finance | Vended Program Contract Executed or Food and Milk Vendors Contracts Executed |  | Discussion
June | Operations (Lead Admin) | Crisis Management Plan (review with your local emergency responders the summer before opening; start early as a quality plan will take several months to develop) (plan should include training materials, quick reference guide, evacuation maps, recovery plan, roles of incident team personnel, communication plan, and drill tracking document) | Y | PCSC will need a copy of your "Incident Team" org chart with roles defined and your "Recovery Plan" timeline. We will also need to be included on your emergency notification system (whether that is text system, phone tree, or email distribution system).
June | Finance | Charter School Advanced Payment Request Awareness |  | Contact SDE
June | Finance | Transportation Advance Payment Request Awareness |  | Contact SDE
June | Special Populations | Special Education Assurances Filed with SDE Awareness |  | Contact SDE
June | Operations (Lead Admin) | Formal Reporting with Federal Programs Department is due in June for the upcoming school year. |  | Discussion
June | Operations (Lead Admin) | Building Reconfiguration Form: anytime a school changes the grade levels served, or makes a significant change to the building this form needs to be filed with the Idaho School Safety ad Security department of the Division of Building Safety. |  | Contact Mike Munger
June | Operations (Lead Admin) | Review Reporting Requirements |  | Document Review
June | Operations (Lead Admin) | Review Website Requirements |  | Document Review
June | Operations (Lead Admin) | Review PCSC Performance Framework |  | Document Review
June | Finance | Primary Curriculum Materials (for core subjects and model specific) |  | Discussion in June; Site Visit Observation in Aug
June | Finance | Curriculum Support Materials (counters, etc.) |  | Discussion in June; Site Visit Observation in Aug
June | Finance | Classroom Consumables (markers, paper) |  | Discussion in June; Site Visit Observation in Aug
June | Finance | Maintenance Consumables (cleaning supplies, paper towels) |  | Discussion in June; Site Visit Observation in Aug
June | Finance | Office Consumables (paper, folders) |  | Discussion in June; Site Visit Observation in Aug
June | Finance | Kitchen non-food consumables (napkins, disposable products, gloves) |  | Discussion in June; Site Visit Observation in Aug
June | Enrollment (Registrar) | Student Data uploaded to SIS |  | Discussion
June | Operations (Lead Admin) | Background Checks are completed for all staff (please explain what service is used for employees and if alternative service is used for volunteers; also address the process) |  | If this process is not documented in the family and employee handbook additional evidence will need to be provided.
June | Operations (Lead Admin) | Teacher License verification |  | Discussion of Process and record keeping.
June | Special Populations | Record Keeping plan is established for Special Education |  | Document Review (file checklist, tracking forms, etc. Whatever kind of documentation speaks to your plan)
June | Operations (Lead Admin) | Annual Budget Submitted to SDE/PCSC | Y | meeting minutes documenting approval | 33-801
August | Finance | Primary Curriculum Materials (for core subjects and model specific) |  | Observation
August | Finance | Curriculum Support Materials (counters, etc.) |  | Observation
August | Finance | Classroom Consumables (markers, paper) |  | Observation
August | Finance | Maintenance Consumables (cleaning supplies, paper towels) |  | Observation
August | Finance | Office Consumables (paper, folders) |  | Observation
August | Finance | Kitchen non-food consumables (napkins, disposable products, gloves) |  | Observation
August | Enrollment (Registrar) | Student Data uploaded to SIS and compatibility with ISEE verified |  | Review
August | Operations (Lead Admin) | Background Checks are completed for all staff and volunteer background check procedures are outlined for a parent audience |  | Document Review (excerpts from employee and family handbook)
August | Operations (Lead Admin) | Teacher License verification (this is due to SDE via ISEE by 10/17) |  | Discussion of Process and record keeping.
August | Operations (Lead Admin) | Variance request/ hard to fill positions |  | Contact SDE if necessary
August | Academics | Curriculum Map for first year |  | Document Review / Discussion
August | Academics | First two weeks curriculum plan process |  | Document Review / Discussion
August | Operations (Lead Admin) | IT coordinator is identified and sufficiently trained or Contracted Services has been retained |  | Discussion regarding qualifications and duties.
August | Operations (Lead Admin) | Classroom equipment is operational for teacher use (computers, projectors, doc cams, etc.) |  | Observation
August | Operations (Lead Admin) | Equipment is operational for student use (computers, network, logins set up, etc.) |  | Observation
August | Operations (Lead Admin) | Internet Access functional and sufficient |  | Observation
August | Operations (Lead Admin) | facilities safety checklists (indoor and outdoor) established |  | Document Review
August | Operations (Lead Admin) | allergies accounted for |  | Document Review / Observation of any accommodated eating space
August | Operations (Lead Admin) | Health Inspection Passed and Filed | Y | Document Review
August | Operations (Lead Admin) | Fire Inspection Passed and Filed | Y | Document Review
August | Operations (Lead Admin) | Occupancy Certificate Posted | Y | Document Review
August | Operations (Lead Admin) | Building Safety Inspection Posted | Y | Document Review
August | Operations (Lead Admin) | Security Plan as applicable(cameras, secured areas/doors, doors labeled for visitors, etc.) |  | Observation
August | Operations (Lead Admin) | Key Distribution Record |  | Document Review
August | Operations (Lead Admin) | student space staging is complete prior to back to school night (classrooms and common spaces), age appropriate, and meets needs of model |  | Observation
August | Operations (Lead Admin) | special populations areas are prepared (variety of spaces and record security) |  | Observation
August | Operations (Lead Admin) | employee work room prepared |  | Observation
August | Operations (Lead Admin) | outdoor play space prepared |  | Observation
August | Enrollment (Registrar) | Student File Compliance Check |  | Student file spot check

## Meeting 1 - Oct.
Public Charter School Commission Pre-Operational School Meeting #1
| Date of Meeting: | School Attendees: |  | PCSC Attendees:
Facilities plan is on track for opening | Facilities Notes:
Y / N
CATEGORY | TOPIC | COPY FOR PCSC | EVIDENCE FOR REVIEW | COMMENTS | VERIFICATION
Finance | Performance Certificate executed. Please note, any adjustments the board may want to make to this content require an amendment of the certificate. Contact Kirsten Pochop with questions. | Y | Fully executed copy on file with the PCSC.
Governance | Bylaws executed. | Y | Executed copy of bylaws and meeting minutes evidencing adoption
Governance | Articles of Incorporation (to be filed with Secretary of State) | Y | Executed Copy. PCSC will verify this online.
Governance | Board Term Sheet/ Conflict of Interest Statement / Code of Ethics (33-5200 ; 74-404) | Y | Signed by Each Board Director
Governance | Independent Legal Counsel Secured | Y | Meeting Minutes evidencing Approval of Engagement
Governance | 501c3 (file the IRS form 1023. This is a lengthy application and costs approx. $1K. Please work with your legal counsel.) For planning purposes - the 1023 application requires that documentation such as executed bylaws, conflict, and articles of incorporation are already finalized. | Y | Approval or Interim Approval letter from the IRS (the final letter can take months to arrive, for most purposes the interim letter is sufficient)
Governance | Notification to Office of State Board of Education of Petition Approval. This is required by statute to come from the school board. Please address to Alison Henken (alison.henken@osbe.idaho.gov) and cc Jenn Thompson (jenn.thompson@osbe.idaho.gov). |  | Discussion.
Operations (Lead Administrator) | Review procurement requirements and ensure your school proceeds appropriately. This is necessary for nutrition, transportation, IT, and other large purchases. I.C. 67-2806; see also a good summary from the SDE's Nutrition program here: https://www.sde. |  | Discussion
Operations (Lead Administrator) | Meet with Building Safety Team - all schools are evacuated on safety and security every 3 years. The resulting report provided by the Department of Building Safety is a confidential document between the school board and the DBS. All schools are evaluated every year on building maintenance, safety and egress. They review based on 650 points of assessment, presenting a graphic to help your team make informed decisions about financial investments. (hint - the answer is not cameras). Contact Mike within 60 days of opening to have an early discussion on safety concerns as you begin your facilities project. |  | Discussion. Mike Munger School Safety Analysist Office of School Safety and Security - mike.munger@dbs.idaho.gov | Would you like me to try to schedule this as part of the December pre-opening meeting?
LOOKING FORWARD
Governance | New School Form. This form is available from Michelle Clement Taylor and due to her in January. This form establishes your school and LEA operational numbers with the SDE and ensures you are eligible to received funds. You'll need your EIN and DUNS numbers complete before you submit this document. |  | Discussion
Enrollment (Registrar) | Comprehensive Recruitment Plan |  | Discussion
Enrollment (Registrar) | Compliant and Accessible Student Enrollment Application (considers potential language barriers and/or access to technology as well as efficiency and security of data collection) |  | Discussion
Operations (Lead Administrator) | Consider a 5-Year IT plan |  | Discussion
Operations (Lead Administrator) | It is recommended that you begin working on a transportation plan now. The procurement process is lengthy and many charters experience difficulty with bus and driver shortages. |  | Discussion
Governance | Review board training expectations and timeline. Evidence that all board members have completed the required trainings as well as a presentation of a year 1 plan are due in April. |  | Discussion
Special populations | Intro to the Special Education Readiness review will be conducted by the SDE in the August before you open. This is based on the Special Education Manual. We will review this with the board in October and again in April. Please ensure that your board has read this documentation and that the school is fully prepared (including adopted board policy, child find and RtI programs, appropriate forms, and new student records review). |  | Discussion
Governance | Policy Development. School boards must adopt a full scope of policies. A full collection of policies are available from the ISBA with membership. (charter specific, reviewed 2018, but still need full review and minor adaptation from the board. ISBA recommends this process take several months). |  | Discussion
Operations (Lead Administrator) | Website Development. A few items are required to be posted regularly on your website. This is evaluated every year and reflected on your annual report. |  | Discussion.
Governance | School Leader Evaluation Process. The SDE has required tools and procedures. We will revisit this in April. |  | Discussion.
Operations (Lead Administrator) | Wellness Plan/ Policy (required for NSLP compliance, but not until July after first op year. Recommended that you get this in place asap as it can be positive leverage for grants and will be easier to implement from the beginning). See SDE descriptions and resources here: http://www.sde.idaho.gov/cnp/hne/wellness.html |  | Discussion | Eligibility Manual for School Meals
Overall Meeting Comments:

## Meeting 2 - Dec.
Public Charter School Commission Pre-Operational School Meeting #2
| Date of Meeting: | School Attendees: |  | PCSC Attendees:
Facilities plan is on track for opening | Facilities Notes:
Y / N
CATEGORY | TOPIC | COPY FOR PCSC | EVIDENCE FOR REVIEW | COMMENTS | VERIFICATION
Finance | Finance Policy review, particularly internal controls. | Y | Document Review
Finance | Bank Account Established |  | Discussion
Finance | Signatories Identified (best practice is 2 required, but 3 identified) |  | Meeting minutes evidencing appointment.
Finance | salary scale developed (considers fair hiring practices and local hiring competition) |  | Discussion of Plan
Finance | EIN number established (state Tax ID number) |  | Verify Number exists
Finance | DUNS number established (required for eligibility to receive government dollars) |  | Verify Number exists
Enrollment (Registrar) | Comprehensive Recruitment Plan |  | Discussion of Plan
Enrollment (Registrar) | Compliant and Accessible Student Enrollment Application (considers potential language barriers a/o access to technology as well as efficiency and security of data collection). | Y | Discussion of Plan | SDE has a template for this form
Operations (Lead Administrator) | Staffing plan should be fully established and comprehensive. This should reflect enrollment projections, anticipated demographics, model specific needs, and budgets. It should also include clear trigger points for hiring prior to the first year (i.e. how will you know you can hire a 2nd teacher or a counselor and how will you balance that with the natural hiring season?) |  | Discussion of Plan (recording on dashboard tab) | See IDAPA 08.02.02 for staffing certification needs
Operations (Lead Administrator) | job descriptions for general positions are generally representative of duties. A full collection of job descriptions are available from the ISBA with membership. |  | Document Review | See IDAPA 08.02.02 for staffing certification needs
Operations (Lead Administrator) | Release of Information on Past Job Performance. Ensure that you have a plan for checking references and documenting fair hiring practices, prior to hiring any employee (including admin). This generally includes board adoption of policy before you can interview. |  | Document review | 33-1210
Operations (Lead Administrator) | Provide an update on the schools technology plan/progress. |  | Discussion of Plan | Erate Flow chart
Operations (Lead Administrator) | Stakeholders must have adequate access to appropriate school personnel. Many schools adopt communication/grievance procedures that include clear documentation. This will also require that the staff reporting structure is clear. | Y | A copy of the school's org chart will need to be provided to the PCSC for our files. The PCSC will also verify that grievance procedures and contact information is appropriately noted on your website.
Operations (Lead Administrator) | Curriculum Selection Process (should evidence research and stakeholder input as well as a plan for regular review regarding efficacy) |  | Discussion of Plan | consider: IC 33-512A
Academics | data analysis / Assessment plan |  | Discussion of Plan
Special Populations | Home Language Survey (a section of the registration paperwork) SDE has a state wide required document. |  | Document Review | http://www.sde.idaho.gov/el-migrant/el/index.html
Governance | Board Meeting Calendar (high level evidence that the board is planning for key work such as, administrator evaluation process, academic performance review, the audit report, etc.) |  | Document Review
Governance | Job Descriptions for Board Officers (chair, secretary, treasurer, etc.) and Committees (governance, academic, finance, etc.) |  | Document Review
Governance | Meeting Agendas posted Accurately |  | Process and Document Review | Open Meetings Law
Governance | Board Meeting Minutes (format consistent, content sufficient, see open meetings law) | Y | Several Examples will be required throughout the pre-operational year
Governance | Board Member Succession, Orientation, and Termination Process |  | Process review based on bylaws.
LOOKING FORWARD
Enrollment (Registrar) | Review the enrollment procedures guidance document and ensure timelines are in place and planned procedures are compliant. |  | Discussion
Operations (Lead Administrator) | Business Manager Hired |  | Discussion
Operations (Lead Administrator) | Administrator hired (process needs to evidence fair hiring practices) |  | Process or Policy Review
Overall Meeting Comments:

## Meeting 3 - Feb.
Public Charter School Commission Pre-Operational School Meeting #3
| Date of Meeting: | School Attendees: |  | PCSC Attendees:
Facilities plan is on track for opening | Facilities Notes:
Y / N
CATEGORY | TOPIC | COPY FOR PCSC | EVIDENCE FOR REVIEW |  | COMMENTS | VERIFICATION
Governance | Policy adoption progress review. Bring copies/ or digital access to all board approved policies to date. | Y | Document Review
Finance | PO Process Outlined (for admin, board, and staff if different) |  | Discussion of Plan
Finance | reimbursement request forms and process established |  | Document Review
Enrollment (Registrar) | Records Request process. It is common to include the reference to the applicable statute on the document. See I.C. 33-209 |  | Document Review | Does Michelle have an example of this?
Finance | Kitchen Capital Purchases (warming ovens, smallwares, etc.). Contact the SDE Nutrition department to ensure your planned service area meets the requirements for food safety, serving, and point of sale. |  | Discussion
Enrollment (Registrar) | Notification of lottery date posted |  | PCSC Staff will verify this on school's website
Enrollment (Registrar) | First offer notification and expiration process is developed. |  | Discussion/Document Review
Enrollment (Registrar) | Registration paperwork is compliant |  | Document Review
Enrollment (Registrar) | Student record receipt and processing practices should be ready to go. This will be a significant amount of time after the lottery, and it will matter that you have clear procedures before you begin |  | Discussion | health and welfare can provide training to schools regarding immunizations.
Operations (Lead Administrator) | salaried contract established and compliant |  | Document Review
Operations (Lead Administrator) | hourly contract established and compliant |  | Document Review
Operations (Lead Administrator) | Time-off request forms/ process developed |  | Document Review
Operations (Lead Administrator) | playground safe practices outlined (student expectations for outdoor play and supervision plan/expectations. Document should reflect how this information is presented to teachers/students or playground attendants) |  | Document Review | Resources: https://schoolsafety.dbs.idaho.gov/repository/playgrounds/
Operations (Lead Administrator) | medical administration plan (policy recommended; documents should include statement of policy, administration tracking chart, and parent signature line. Options for nurse/admin administration as well as student self admin - i.e. diabetes, inhaler, or epi pen) |  | Document and Process review
Operations (Lead Administrator) | Contact the Federal Programs Office (Elmira Feather) at the SDE and notify them of your school's primary contact. They will get you set up with a login in for their system. In March you'll provide an estimate of low income students and in April you'll be able to see an estimated allocation. If you choose to take this allocation, formal reporting is due by end of June. |  | Discussion
Finance | Annual Budget Approval Process Review the SDE template for newspaper publication. Must have a hearing 30 days prior to the July regular meeting for each school. Board must be approved in July and is due to the PCSC and the SDE by July 15th. SDE require
Operations (Lead Administrator) | Materials Safety Data Sheet (MSDS) utilized appropriately through the school (any chemicals need to be stored appropriately and usage must be tracked according to these guidelines. Mostly applies to chemistry supplies, but may also apply to janitorial or art supplies. This will matter for fire safety and health inspections. verify that your school is compliant if applicable) |  | Document and Process review (if applicable)
LOOKING FORWARD
Enrollment (Registrar) | SIS system set up. Review of ISEE report data and report due dates. Be prepared to begin building a calendar of reminders for the upcoming school year. |  | Discussion
Finance | Facility Lease or Mortgage Executed | Y | Fully Executed Copy on File at PCSC and School
Finance | Accounting System Secured and Set up |  | Discussion
Enrollment (Registrar) | Records tracking for special services process
Operations (Lead Administrator) | Asset tracking and Materials Receipt Process |  | Discussion
Enrollment (Registrar) | Student File Compliance Check |  | Student File plan review/feedback; file spot check in August
Operations (Lead Administrator) | facilities safety checklists (indoor and outdoor) established |  | Document Review
Operations (Lead Administrator) | Crisis Management Plan (review with your local emergency responders the summer before opening; start early as a quality plan will take several months to develop) (plan should include training materials, quick reference guide, evacuation maps, recovery plans. resources can be found here. | Y | PCSC will need a copy of your "Incident Team" org chart with roles defined and your "Recovery Plan" timeline. We will also need to be included on your emergency notification system (whether that is text system, phone tree, or email distribution system). | Include also, a plan for youth suicide prevention and safe and drug free schools. Guidance on both topics can be found here: http://www.sde.idaho.gov/student-engagement/index.html
Operations (Lead Administrator) | drop off and dismissal procedures established (evidence should reflect how this information is shared with families as well as supervision expectations) . The PCSC can provide resources. |  | Document Review
Overall Meeting Comments:

## Meeting 4 - April
Public Charter School Commission Pre-Operational School Meeting #4
| Date of Meeting: | School Attendees: |  | PCSC Attendees:
Facilities plan is on track for opening | Facilities Notes:
Y / N
CATEGORY | TOPIC | COPY FOR PCSC | EVIDENCE FOR REVIEW | COMMENTS |  | VERIFICATION
Governance | Policy adoption progress review. Bring copies/ or digital access to all board approved policies to date. | Y | Document Review
Enrollment (Registrar) | Student information system implementation update |  | Discussion
Operations (Lead Administrator) | payroll and timecard systems adopted |  | Discussion
Operations (Lead Administrator) | Substitute process established |  | Discussion
Operations (Lead Administrator) | Health Benefits Secured |  | Discussion
Operations (Lead Administrator) | Retirement Benefits Secured |  | Discussion
Operations (Lead Administrator) | New Hire Process Established (paperwork, legal, payroll, benefits, etc.) |  | Document Review. A sample new-hire checklist is sufficient.
Operations (Lead Administrator) | New Hire Orientation Established (should consider certified and classified staff and evidence plans for beginning of year as well as mid-year hires) |  | Discussion
Operations (Lead Administrator) | PCSC Reporting Calendar Reviewed |  | Discussion
Operations (Lead Administrator) | SDE Reporting Calendar Reviewed and Special Education, and OSBE |  | Discussion | Special Education: http://www.sde.idaho.gov/sped/files/shared/Special-Education-Important-Dates.pdf OSBE: Continuous Improvement Plan; Literacy Intervention program Plan, and College and Career Advising and Mentoring Plan https://boardofed.idaho.gov/k-12-education/school-district-charter-school-planning-training/; ISEE Data Monthly Submission Schedules: https://www.sde.idaho.gov/tech-services/isee/files/general/program/Data-Monthly-Submission-Schedules.pdf
Operations (Lead Administrator) | Stakeholder Reporting Calendar Established (should evidence report cards, state of the school address, stakeholder survey timelines, etc.) |  | If this type of information is embedded in your published school calendar, no further evidence is necessary.
Operations (Lead Administrator) | Principal's Repot (to Board) Plan (i.e. data dashboard) Best practices include a standard set of data reported to the governing board by the school principal each meeting. This data should reflect progress toward established goals, and attempt to reflect the board's administrator evaluation process. |  | Discussion of Plan/ Document Review
Operations (Lead Administrator) | Community Meeting Plan (assemblies) |  | If this information is embedded in your daily schedule, no further evidence is required. If not, discussion.
Operations (Lead Administrator) | Community Event Plan (student work showcases, conferences, etc.) |  | if this information is embedded in your published school calendar, no further evidence is necessary. If not, discussion.
Academics | school-wide professional development plan (should include plus with time sufficiently reflected in the calendar and daily schedule) |  | Document Review | 08.02.02 includes some specific requirements.
Academics | Teacher coaching plan (reflecting how individual needs will be met beyond the school-wide PD plan) |  | Document Review
Academics | Teacher formal evaluation tools |  | Document Review | 08.02.02
Special Populations | Special Education Director Identified |  | Discussion regarding qualifications, start date, and plan for student intake and paras.
Special Populations | 504 coordinator identified |  | Discussion regarding qualifications, start date, and time allocation
Operations (Lead Administrator) | NSLP application approved (if applicable) |  | Discussion
Operations (Lead Administrator) | common behaviors description are communicated. (transitions, bathrooms, cafeteria, etc.) |  | Document Review
Operations (Lead Administrator) | Positive Behavior Plan (this is in extension of the formal discipline policies and should evidence the school's day to day philosophy and procedures for classroom management) |  | Document Review
Operations (Lead Administrator) | Annual Calendar | Y | Board Approved Final Copy
Operations (Lead Administrator) | Daily Schedule | Y | Board Approved Final Copy
Operations (Lead Administrator) | Extra Curricular Plan Established (if applicable) |  | Discussion
Operations (Lead Administrator) | After school Care Plan Established (if applicable) |  | Discussion
Operations (Lead Administrator) | Review the estimated federal programs allocation, provided by the federal programs department and decide whether you intend to pursue the funds. |  | Discussion
Operations (Lead Administrator) | Website Compliance Check |  | PCSC will verify online at various times
Special Populations | Review of readiness for special education. | Y | Please bring meeting minutes evidencing adoption of the special education manual and special education policies, copies of all policies, forms. You may want to bring your special education director (or intended) to this meeting to discuss plans for staff training and records review. |  | IEP Guidance Handbook
Governance | Board Member Training | Y | Evidence that all board members have completed the required trainings and a copy of the year 1 development plan is due to the PCSC
Operations (Lead Administrator) | Building maintenance safety check |  | https://schoolsafety.dbs.idaho.gov/10yearplans/
LOOKING FORWARD
Academics | Curriculum Map for first year (minimally) | Y | Document Review
Finance | Consolidated Federal and State Grant Applications. Contact SDE- Elmira Feather, due on 5/1. |  | Discussion
Governance | New Charter School Boot camp. Admin, Business Manager, program directors, and board members are invited, please talk with Michelle Clement-Taylor for more information. |  | Discussion
Academics | First two weeks curriculum plan process |  | Document Review
Overall Meeting Comments:

## Meeting 5 - June
Public Charter School Commission Pre-Operational School Meeting #5
| Date of Meeting: | School Attendees: |  | PCSC Attendees:
Facilities plan is on track for opening | Facilities Notes:
Y / N
CATEGORY | TOPIC | COPY FOR PCSC | EVIDENCE FOR REVIEW | COMMENTS | VERIFICATION
Special Populations | Review of Special Education Readiness Plan (including child find, RtI, and at-risk identification procedures) |  | Discussion of Plan/ Document Review
Governance | School Leader Evaluation Tools | Y | Document (if modified from SDE)
Finance | Transportation Contract Executed |  | Meeting Minutes evidencing contract award or authorization for signatory
Finance | Landscaping/Snow Removal Contract Executed |  | Meeting Minutes evidencing contract award or authorization for signatory
Finance | Special Services (speech, OT, etc.) Identified and retained |  | Meeting Minutes evidencing contract award or authorization for signatory
Finance | Independent Auditor Contract Executed |  | Meeting Minutes evidencing contract award or authorization for signatory
Finance | IT Contract Executed (if applicable) |  | Meeting Minutes evidencing contract award or authorization for signatory
Finance | D&O Insurance Policy Secured | Y | Meeting Minutes evidencing contract award or authorization for signatory.
Finance | Property and Liability Insurance Secured |  | Meeting Minutes evidencing contract award or authorization for signatory
Finance | Workers Compensation Insurance Secured |  | Meeting Minutes evidencing contract award or authorization for signatory
Finance | monthly finance reports established for board |  | Document Review
Enrollment (Registrar) | Family orientation process |  | Discussion
Enrollment (Registrar) | New student beginning of year process |  | Discussion
Enrollment (Registrar) | New student mid-year process |  | Discussion
Enrollment (Registrar) | Records tracking for special services process |  | Discussion
Academics | Assessment Coordinator Identified |  | Discussion regarding qualifications, start date, and sufficient time allocation.
Operations (Lead Administrator) | Asset tracking and Materials Receipt Process |  | Discussion
Special Populations | ELL coordinator identified |  | Discussion regarding qualifications, start date, and plans for reviewing student records.
Operations (Lead Administrator) | drop off and dismissal procedures established (evidence should reflect how this information is shared with families as well as supervision expectations) |  | Discussion
Operations (Lead Administrator) | FRL application process established |  | Discussion
Finance | Vended Program Contract Executed or Food and Milk Vendors Contracts Executed |  | Discussion
Operations (Lead Administrator) | Crisis Management Plan (review with your local emergency responders the summer before opening; start early as a quality plan will take several months to develop) (plan should include training materials, quick reference guide, evacuation maps, recovery plan, roles of incident team personnel, communication plan, and drill tracking document) | Y | PCSC will need a copy of your "Incident Team" org chart with roles defined and your "Recovery Plan" timeline. We will also need to be included on your emergency notification system (whether that is text system, phone tree, or email distribution system).
Finance | Charter School Advanced Payment Request Awareness |  | Contact SDE
Finance | Transportation Advance Payment Request Awareness |  | Contact SDE
Special Populations | Special Education Assurances Filed with SDE Awareness |  | Contact SDE
Operations (Lead Administrator) | Formal Reporting with Federal Programs Department is due in June for the upcoming school year. |  | Discussion
Operations (Lead Administrator) | Building Reconfiguration Form: anytime a school changes the grade levels served, or makes a significant change to the building this form needs to be filed with the Idaho School Safety ad Security department of the Division of Building Safety. |  | Contact Mike Munger
Operations (Lead Administrator) | Review Reporting Requirements |  | Document Review
Operations (Lead Administrator) | Review Website Requirements |  | Document Review
Operations (Lead Administrator) | Review PCSC Performance Framework |  | Document Review
LOOKING FORWARD
Finance | Primary Curriculum Materials (for core subjects and model specific) |  | Discussion in June; Site Visit Observation in Aug
Finance | Curriculum Support Materials (counters, etc.) |  | Discussion in June; Site Visit Observation in Aug
Finance | Classroom Consumables (markers, paper) |  | Discussion in June; Site Visit Observation in Aug
Finance | Maintenance Consumables (cleaning supplies, paper towels) |  | Discussion in June; Site Visit Observation in Aug
Finance | Office Consumables (paper, folders) |  | Discussion in June; Site Visit Observation in Aug
Finance | Kitchen non-food consumables (napkins, disposable products, gloves) |  | Discussion in June; Site Visit Observation in Aug
Enrollment (Registrar) | Student Data uploaded to SIS |  | Discussion
Operations (Lead Administrator) | Background Checks are completed for all staff (please explain what service is used for employees and if alternative service is used for volunteers; also address the process) |  | If this process is not documented in the family and employee handbook additional evidence will need to be provided.
Operations (Lead Administrator) | Teacher License verification |  | Discussion of Process and record keeping.
Special Populations | Record Keeping plan is established for Special Education |  | Document Review (file checklist, tracking forms, etc. Whatever kind of documentation speaks to your plan)
Operations (Lead Administrator) | Annual Budget Submitted to SDE/PCSC | Y | meeting minutes documenting approval | 33-801
Overall Meeting Comments:

## Final Facilities Visit - Aug.
Public Charter School Commission Pre-Operational School Meeting #6
| Date of Meeting: | School Attendees: |  | PCSC Attendees:
CATEGORY | TOPIC | COPY FOR PCSC | EVIDENCE FOR REVIEW | COMMENTS | VERIFICATION
Finance | Primary Curriculum Materials (for core subjects and model specific) |  | Observation
Finance | Curriculum Support Materials (counters, etc.) |  | Observation
Finance | Classroom Consumables (markers, paper) |  | Observation
Finance | Maintenance Consumables (cleaning supplies, paper towels) |  | Observation
Finance | Office Consumables (paper, folders) |  | Observation
Finance | Kitchen non-food consumables (napkins, disposable products, gloves) |  | Observation
Enrollment (Registrar) | Student Data uploaded to SIS and compatibility with ISEE verified |  | Review
Operations (Lead Administrator) | Background Checks are completed for all staff and volunteer background check procedures are outlined for a parent audience |  | Document Review (excerpts from employee and family handbook)
Operations (Lead Administrator) | Teacher License verification (this is due to SDE via ISEE by 10/17) |  | Discussion of Process and record keeping.
Operations (Lead Administrator) | Variance request/ hard to fill positions |  | Contact SDE if necessary
Academics | Curriculum Map for first year |  | Document Review / Discussion
Academics | First two weeks curriculum plan process |  | Document Review / Discussion
Operations (Lead Administrator) | IT coordinator is identified and sufficiently trained or Contracted Services has been retained |  | Discussion regarding qualifications and duties.
Operations (Lead Administrator) | Classroom equipment is operational for teacher use (computers, projectors, doc cams, etc.) |  | Observation
Operations (Lead Administrator) | Equipment is operational for student use (computers, network, logins set up, etc.) |  | Observation
Operations (Lead Administrator) | Internet Access functional and sufficient |  | Observation
Operations (Lead Administrator) | facilities safety checklists (indoor and outdoor) established |  | Document Review
Operations (Lead Administrator) | allergies accounted for |  | Document Review / Observation of any accommodated eating space
Operations (Lead Administrator) | Health Inspection Passed and Filed | Y | Document Review
Operations (Lead Administrator) | Fire Inspection Passed and Filed | Y | Document Review
Operations (Lead Administrator) | Occupancy Certificate Posted | Y | Document Review
Operations (Lead Administrator) | Building Safety Inspection Posted | Y | Document Review
Operations (Lead Administrator) | Security Plan as applicable(cameras, secured areas/doors, doors labeled for visitors, etc.) |  | Observation
Operations (Lead Administrator) | Key Distribution Record |  | Document Review
Operations (Lead Administrator) | student space staging is complete prior to back to school night (classrooms and common spaces), age appropriate, and meets needs of model |  | Observation
Operations (Lead Administrator) | special populations areas are prepared (variety of spaces and record security) |  | Observation
Operations (Lead Administrator) | employee work room prepared |  | Observation
Operations (Lead Administrator) | outdoor play space prepared |  | Observation
Enrollment (Registrar) | Student File Compliance Check |  | Student file spot check
Overall Meeting Comments: